## Tasks
Task ID | WBS Level | Task Name | Owner | Status | Start Date | End Date | Progress % | Dependency
T001 | 1 | Project Initiation | PMO | Completed | 2026-01-01 | 2026-01-15 | 100 | -
T002 | 2 | Requirements Gathering | Business Analyst | Completed | 2026-01-05 | 2026-01-25 | 100 | T001
T003 | 2 | Solution Design | IT Architect | Completed | 2026-01-20 | 2026-02-10 | 100 | T002
T004 | 3 | CRM Configuration | IT Team | In Progress | 2026-02-11 | 2026-03-15 | 60 | T003
T005 | 3 | Data Migration | Data Team | In Progress | 2026-02-20 | 2026-03-25 | 40 | T003
T006 | 3 | Integration Setup | IT Team | Not Started | 2026-03-01 | 2026-03-30 | 0 | T004
T007 | 4 | User Training | Training Team | Not Started | 2026-03-15 | 2026-04-10 | 0 | T004
T008 | 4 | UAT Testing | QA Team | Not Started | 2026-04-01 | 2026-04-20 | 0 | T006
T009 | 5 | Go-Live | Project Team | Not Started | 2026-05-01 | 2026-05-03 | 0 | T008
T010 | 5 | Hypercare Support | PMO | Not Started | 2026-05-02 | 2026-06-15 | 0 | T009